## ~output
RANGE_VALUE | DATE_USED_FOR_RANGE | WOR_WORKS_ORDER_NO | DEFECT_ID | DEF_DEFECT_CODE | DEF_PRIORITY | DEF_INSPECTION_DATE | DEF_DEFECT_DESCR | CONTRACT | WO_PRO_STAT | EOT_STATUS | WOR_NUM_ATTRIB10 | REQ_EOT_DATE | REC_EOT_DATE | WOL_DEF_DEFECT_ID | WO Process Status | EOT Reason for Request | EOT Reason for Rejection | WO Reason for Hold | WO Reason for Rejection | WOR_CHAR_ATTRIB100 | WOR_DATE_ATTRIB127 | WOR_EST_COMPLETE | Works Order Originator | DUE_DATE | DAYS | ACT_CODE | WOL_REP_ACTION_CAT | TARGET_DATE | WORK_ORDER_STATUS | WO_RAISED_BY | WOR_CONTACT | WOR_DATE_CONFIRMED | WOR_ACT_COST | WOR_EST_COST | WOR_DATE_RAISED | WOL_DATE_COMPLETE | WOL_DATE_REPAIRED | BUDGET_CODE | ICB_WORK_CATEGORY_NAME
0-1 | 2013-05-04 09:55 | NE1_HLSR/86 | 428729 | POTH | 1 | 2013-04-04 09:55 |  | HLSR | INS | REJ | 1060 | 2013-06-04 |  | 428729 | INS | UTL | PRG |  |  | INS |  | 2013-05-04 09:55 | SYSTEM ADMINISTRATOR | 2013-06-04 09:55 | 1 | MC | T | 2013-05-04 09:55 | INSTRUCTED | SYSTEM ADMINISTRATOR |  | 2013-04-04 10:00 |  | 26.43 | 2013-04-04 09:57 |  |  | RA0999 | NE Reactive Activity Lump Sum Defect Rectification
2013-01-03 | 2013-07-04 | NE1_HLSR/83 | 428726 | CWAY | 1 | 2013-04-04 09:43 |  | HLSR |  | APF | 1060 | 2013-07-04 |  | 428726 |  | UTL | [5 empty] | 2013-05-04 09:43 | SYSTEM ADMINISTRATOR | 2013-07-04 | 1 | MS | T | 2013-07-04 | INSTRUCTED | SYSTEM ADMINISTRATOR |  |  |  | 26.43 | 2013-04-04 09:46 |  |  | RA0999 | NE Reactive Activity Lump Sum Defect Rectification
2013-03-10 | 2013-10-04 15:22 | NE1_HLSR/75 | 428716 | DAMM | 2H | 2013-03-04 15:22 | Test Defect | HLSR | INS |  |  |  |  | 428716 | INS |  |  |  |  | INS |  | 2013-10-04 15:22 | LOHACNE1 | 2013-11-04 15:22 | 7 | BT | P | 2013-10-04 15:22 | INSTRUCTED | LOHACNE1 |  | 2013-03-04 16:22 |  | 26.43 | 2013-03-04 16:21 |  |  | RA0999 | NE Reactive Activity Lump Sum Defect Rectification
2013-03-10 | 2013-11-04 09:34 | NE1_HLSR/82 | 428725 | POTH | 2H | 2013-04-04 09:34 |  | HLSR | INS |  |  |  |  | 428725 | INS |  |  |  |  | INS |  | 2013-11-04 09:34 | SYSTEM ADMINISTRATOR | 2013-12-04 09:34 | 7 | MC | P | 2013-11-04 09:34 | INSTRUCTED | SYSTEM ADMINISTRATOR |  | 2013-04-04 09:38 |  | 5.33 | 2013-04-04 09:37 |  |  | RA0999 | NE Reactive Activity Lump Sum Defect Rectification
2013-03-10 | 2013-10-04 | NE1_HLSR/85 | 428728 | ACCD | 2H | 2013-04-04 09:51 |  | HLSR |  | CND | 1060 | 2013-05-04 | 2013-10-04 | 428728 |  | UTL | [5 empty] | 2013-11-04 09:51 | SYSTEM ADMINISTRATOR | 2013-10-04 | 7 | BT | P | 2013-10-04 | INSTRUCTED | SYSTEM ADMINISTRATOR |  |  |  | 26.43 | 2013-04-04 09:54 |  |  | RA0999 | NE Reactive Activity Lump Sum Defect Rectification
2013-03-10 | 2013-11-04 | NE1_HTO/72 | [5 empty] | HTO | [12 empty] | 2013-11-04 |  | Trainee 03 |  | 0 | 0 |  | 2013-11-04 | DRAFT | Trainee 03 |  |  |  |  | 28/03/2013 11:41:20 |  |  | DU0002 | Highways Task Order Request Dummy Budget
>10 | 18/04/2013 | NE1_HR/37 | 428627 | ACCD | 2H | 25/02/2013 10:41:00 | Test Defect Description | HR | INS | CND | 1060 | 2013-01-03 | 18/04/2013 | 428627 | INS | UTL |  |  |  | INS |  | 2013-04-03 10:41 | Trainee 01 | 18/04/2013 | 7 | FC | P | 18/04/2013 | INSTRUCTED | Trainee 01 | NS | 25/02/2013 |  | 1 | 25/02/2013 11:00:28 |  |  | OM0909 | NE 3rd Party Claims over Â£10k
>10 | 2013-01-05 16:21 | NE1_HLSR/76 | 428719 | CRCK | 2M | 2013-03-04 16:21 |  | HLSR | INS |  |  |  |  | 428719 | INS |  |  |  |  | INS |  | 2013-01-05 16:21 | LOHACNE1 | 2013-02-05 16:21 | 28 | CM | P | 2013-01-05 16:21 | INSTRUCTED | LOHACNE1 |  | 2013-03-04 16:24 |  | 7.44 | 2013-03-04 16:23 |  |  | RA0999 | NE Reactive Activity Lump Sum Defect Rectification
>10 | 2013-01-05 16:24 | NE1_HLSR/77 | 428720 | ACCD | 1E | 2013-03-04 16:24 |  | HLSR | [5 empty] | 428720 | [7 empty] | 2013-01-05 16:24 | LOHACNE1 | 2013-02-05 16:24 | 28 | MC | P | 2013-01-05 16:24 | DRAFT | LOHACNE1 |  |  |  | 5.79 | 2013-03-04 16:25 |  |  | RA0999 | NE Reactive Activity Lump Sum Defect Rectification
>10 | 2013-01-05 16:35 | NE1_HLSR/78 | 428721 | ACCD | 1 | 2013-03-04 16:35 |  | HLSR | INS |  |  |  |  | 428721 | INS |  |  |  |  | INS |  | 2013-03-04 17:35 | LOHACNE1 | 2013-04-04 17:35 | 28 | BT | P | 2013-01-05 16:35 | INSTRUCTED | LOHACNE1 |  | 2013-03-04 16:42 |  | 13.79 | 2013-03-04 16:42 |  |  | RA0999 | NE Reactive Activity Lump Sum Defect Rectification
>10 | 2013-02-05 09:04 | NE1_HLSR/79 | 428722 | ACCD | 1 | 2013-04-04 09:04 |  | HLSR | INS |  |  |  |  | 428722 | INS |  |  |  |  | INS |  | 2013-04-04 10:04 | LOHACNE1 | 2013-05-04 10:04 | 28 | BT | P | 2013-02-05 09:04 | INSTRUCTED | LOHACNE1 |  | 2013-04-04 09:08 |  | 26.43 | 2013-04-04 09:07 |  |  | RA0999 | NE Reactive Activity Lump Sum Defect Rectification
>10 | 2013-02-05 09:20 | NE1_HLSR/81 | 428724 | POTH | 2H | 2013-04-04 09:20 |  | HLSR | INS |  |  |  |  | 428724 | INS |  |  |  |  | INS |  | 2013-02-05 09:20 | LOHACNE1 | 2013-03-05 09:20 | 28 | MC | T | 2013-02-05 09:20 | INSTRUCTED | LOHACNE1 |  | 2013-04-04 09:23 |  | 44.09 | 2013-04-04 09:22 |  |  | RA0999 | NE Reactive Activity Lump Sum Defect Rectification
>10 | 28/04/2013 | NE1_HTO/69 | [5 empty] | HTO | [12 empty] | 28/04/2013 |  | Trainee 11 |  | 0 | 0 |  | 28/04/2013 | DRAFT | Trainee 11 |  |  |  |  | 28/03/2013 11:40:34 |  |  | DU0002 | Highways Task Order Request Dummy Budget
>10 | 28/04/2013 | NE1_HTO/74 | [5 empty] | HTO | [12 empty] | 28/04/2013 |  | Trainee 12 |  | 0 | 0 |  | 28/04/2013 | DRAFT | Trainee 12 |  |  |  |  | 28/03/2013 11:41:20 |  |  | DU0002 | Highways Task Order Request Dummy Budget
>10 | 18/07/2013 | NE1_HTO/68 | [5 empty] | HTO | [12 empty] | 18/07/2013 |  | Trainee 05 |  | 0 | 0 |  | 18/07/2013 | DRAFT | Trainee 05 |  |  |  |  | 28/03/2013 11:41:20 |  |  | DU0002 | Highways Task Order Request Dummy Budget
>10 | 30/04/2013 | NE1_HTO/64 | [5 empty] | HTO | [12 empty] | 30/04/2013 |  | Trainee 08 |  | 0 | 0 |  | 30/04/2013 | DRAFT | Trainee 08 |  |  |  |  | 28/03/2013 11:40:01 |  |  | DU0002 | Highways Task Order Request Dummy Budget
>10 | 27/04/2013 | NE1_HTO/9 | [5 empty] | HTO | [12 empty] | 27/04/2013 |  | Trainee 04 |  | 0 | 0 |  | 27/04/2013 | DRAFT | Trainee 04 |  |  |  |  | 27/02/2013 10:49:21 |  |  | DU0002 | Highways Task Order Request Dummy Budget
>10 | 26/04/2013 | NE1_HTO/71 | [5 empty] | HTO | [12 empty] | 26/04/2013 |  | Trainee 07 |  | 0 | 0 |  | 26/04/2013 | DRAFT | Trainee 07 |  |  |  |  | 28/03/2013 11:40:29 |  |  | DU0002 | Highways Task Order Request Dummy Budget
>10 | 26/04/2013 | NE1_HTO/1 | [5 empty] | HTO | INS | [5 empty] | INS |  |  |  |  | INS | 26/04/2013 |  | Trainee 01 |  | 0 | 0 |  | 26/04/2013 | INSTRUCTED | Trainee 01 | NS - TRANSPORT FOR LONDON | 28/02/2013 |  | 26.43 | 15/02/2013 16:13:59 |  |  | GI0901 | NE General Inspections
>10 | 25/04/2013 | NE1_HTO/63 | [5 empty] | HTO | [12 empty] | 25/04/2013 |  | Trainee 13 |  | 0 | 0 |  | 25/04/2013 | DRAFT | Trainee 13 |  |  |  |  | 28/03/2013 11:21:17 |  |  | DU0002 | Highways Task Order Request Dummy Budget
>10 | 21/04/2013 | NE1_HTO/2 | [5 empty] | HTO | [12 empty] | 21/04/2013 |  | Trainee 01 |  | 0 | 0 |  | 21/04/2013 | DRAFT | Trainee 01 | NS - TRANSPORT FOR LONDON |  |  | 1 | 15/02/2013 16:20:04 |  |  | OM0909 | NE 3rd Party Claims over Â£10k
>10 | 18/04/2013 | NE1_HTO/67 | [5 empty] | HTO | [12 empty] | 18/04/2013 |  | Trainee 02 |  | 0 | 0 |  | 18/04/2013 | DRAFT | Trainee 02 |  |  |  |  | 28/03/2013 11:41:22 |  |  | DU0002 | Highways Task Order Request Dummy Budget
>10 | 28/04/2013 | NE1_HTO/70 | [5 empty] | HTO | [12 empty] | 28/04/2013 |  | Trainee 04 |  | 0 | 0 |  | 28/04/2013 | DRAFT | Trainee 04 |  |  |  |  | 28/03/2013 11:41:22 |  |  | DU0002 | Highways Task Order Request Dummy Budget
>10 | 16/05/2013 | NE1_HTO/66 | [5 empty] | HTO | [12 empty] | 16/05/2013 |  | Trainee 13 |  | 0 | 0 |  | 16/05/2013 | DRAFT | Trainee 13 |  |  |  |  | 28/03/2013 11:41:21 |  |  | DU0002 | Highways Task Order Request Dummy Budget
>10 | 21/05/2013 | NE1_HTO/3 | [5 empty] | HTO | [12 empty] | 21/05/2013 |  | Trainee 01 |  | 0 | 0 |  | 21/05/2013 | DRAFT | Trainee 01 | NS - TRANSPORT FOR LONDON |  |  |  | 15/02/2013 16:24:12 |  |  | OM0909 | NE 3rd Party Claims over Â£10k
>10 | 2013-08-05 | NE1_SR/1 | [5 empty] | SR | [12 empty] | 2013-08-05 |  | Trainee 01 |  | 0 | 0 |  | 2013-08-05 | DRAFT | Trainee 01 |  |  |  |  | 28/03/2013 11:40:35 |  |  | DU0001 | Tunnels & Structures Task Order Request Dummy Budget
Late | 21/02/2013 | NE1_HLSR/1 | 428551 | DAMN | 2H | 14/02/2013 | Defect Description Number 2 | HLSR | [5 empty] | 428551 | [7 empty] | 21/02/2013 | Trainee 01 | 21/02/2013 23:59:59 | 7 | FS | P | 21/02/2013 | DRAFT | Trainee 01 |  |  |  | 26.43 | 14/02/2013 13:37:21 |  |  | RA0999 | NE Reactive Activity Lump Sum Defect Rectification
Late | 14/03/2013 | NE1_HLSR/2 | 428552 | OVER | 2M | 14/02/2013 | Defect Description Number 2 | HLSR | [5 empty] | 428552 | [7 empty] | 14/03/2013 | Trainee 01 | 14/03/2013 23:59:59 | 28 | HT | P | 14/03/2013 | DRAFT | Trainee 01 | NS - TRANSPORT FOR LONDON |  |  | 26.43 | 14/02/2013 13:56:06 |  |  | RA0999 | NE Reactive Activity Lump Sum Defect Rectification
Late | 21/02/2013 | NE1_HLSR/12 | 428554 | OTHR | 2H | 14/02/2013 | Defect Description Number 7 | HLSR | INS |  |  |  |  | 428554 | INS |  |  |  |  | INS |  | 21/02/2013 | Trainee 01 | 21/02/2013 23:59:59 | 7 | CM | P | 21/02/2013 | INSTRUCTED | Trainee 01 | NS - TRANSPORT FOR LONDON | 26/02/2013 |  | 14.24 | 15/02/2013 11:26:57 |  |  | RA0999 | NE Reactive Activity Lump Sum Defect Rectification
Late | 21/02/2013 14:48:00 | NE1_HLSR/9 | 428557 | DAMM | 2H | 14/02/2013 14:48:00 | Test Defect Description on Network 1 | HLSR | INS |  |  |  |  | 428557 | INS |  |  |  |  | INS |  | 21/02/2013 14:48:00 | Trainee 01 | 22/02/2013 14:47:59 | 7 | BF | P | 21/02/2013 14:48:00 | INSTRUCTED | Trainee 01 | NS - TRANSPORT FOR LONDON | 26/02/2013 10:54:46 |  | 26.43 | 15/02/2013 11:22:47 |  |  | RA0999 | NE Reactive Activity Lump Sum Defect Rectification
Late | 2013-07-03 | NE1_HR/5 | 428564 | POTH | 2H | 14/02/2013 16:08:00 | Test Defect Description - Defect and Works Order on Network at XY 2 | HR | INS |  |  |  |  | 428564 | INS |  |  |  |  | INS |  | 21/02/2013 16:08:00 | Trainee 01 | 22/02/2013 16:07:59 | 7 | FC | P | 2013-07-03 | INSTRUCTED | Trainee 01 | NS - TRANSPORT FOR LONDON | 28/02/2013 |  | 26.43 | 14/02/2013 16:09:37 |  |  | OM0909 | NE 3rd Party Claims over Â£10k
Late | 21/02/2013 17:41:00 | NE1_HLSR/3 | 428566 | DAMM | 2H | 14/02/2013 17:41:00 | Test Defect Description on Network at XY with a works order - Test 4 | HLSR | [5 empty] | 428566 | [7 empty] | 21/02/2013 17:41:00 | Trainee 01 | 22/02/2013 17:40:59 | 7 | FB | P | 21/02/2013 17:41:00 | DRAFT | Trainee 01 |  |  |  | 26.43 | 14/02/2013 17:43:14 |  |  | RA0999 | NE Reactive Activity Lump Sum Defect Rectification
Late | 14/03/2013 17:46:00 | NE1_HLSR/5 | 428568 | ACCD | 2M | 14/02/2013 17:46:00 | Test Defect Description on Network at XY with a works order - Test 6 | HLSR | [5 empty] | 428568 | [7 empty] | 14/03/2013 17:46:00 | Trainee 01 | 15/03/2013 17:45:59 | 28 | FS | P | 14/03/2013 17:46:00 | DRAFT | Trainee 01 |  |  |  | 26.43 | 14/02/2013 17:47:24 |  |  | RA0999 | NE Reactive Activity Lump Sum Defect Rectification
Late | 25/03/2013 | NE1_HR/8 | 428570 | COEL | 1A | 15/02/2013 09:59:00 | Test Defect Description Works Order against an asset at XY - Number 2 | HR | INS |  |  |  |  | 428570 | INS |  |  |  |  | INS |  | 15/03/2013 09:59:00 | Trainee 01 | 16/03/2013 09:58:59 | 28 | SE | P | 25/03/2013 | INSTRUCTED | Trainee 01 |  | 25/02/2013 |  | 1 | 15/02/2013 10:00:19 |  |  | OM0909 | NE 3rd Party Claims over Â£10k
Late | 22/02/2013 10:08:00 | NE1_HLSR/6 | 428572 | ACCD | 2H | 15/02/2013 10:08:00 | Test Defect Description Works Order against an asset at XY - Number 4 | HLSR | [5 empty] | 428572 | [7 empty] | 22/02/2013 10:08:00 | Trainee 01 | 23/02/2013 10:07:59 | 7 | FS | P | 22/02/2013 10:08:00 | DRAFT | Trainee 01 | NS - TRANSPORT FOR LONDON |  |  | 1 | 15/02/2013 10:09:46 |  |  | OM0908 | NE Routine Repairs
Late | 15/03/2013 10:22:00 | NE1_HLSR/8 | 428574 | COEL | 1A | 15/02/2013 10:22:00 | Test Defect Description Works Order against an asset at XY - Number 6 | HLSR | [5 empty] | 428574 | [7 empty] | 15/03/2013 10:22:00 | Trainee 01 | 16/03/2013 10:21:59 | 28 | LP | P | 15/03/2013 10:22:00 | DRAFT | Trainee 01 |  |  |  | 1 | 15/02/2013 10:23:11 |  |  | RA0999 | NE Reactive Activity Lump Sum Defect Rectification
Late | 2013-04-04 | NE1_HR/19 | 428575 | DAMG | 2H | 15/02/2013 13:11:00 | Test Defect Description - creation of a works order manually 1 | HR | INS | APF | 1060 | 2013-04-04 |  | 428575 | INS | UTL |  |  |  | INS |  | 22/02/2013 13:11:00 | Trainee 01 | 2013-04-04 | 7 | TS | P | 2013-04-04 | INSTRUCTED | Trainee 01 | NS - TRANSPORT FOR LONDON | 26/02/2013 |  | 1 | 15/02/2013 13:42:00 |  |  | OM0909 | NE 3rd Party Claims over Â£10k
Late | 2013-05-03 | NE1_HR/18 | 428576 | LAMP | 2H | 15/02/2013 13:15:00 | Test Defect Description - creation of a works order manually 2 | HR | INS |  |  |  |  | 428576 | INS |  |  |  |  | INS |  | 22/02/2013 13:15:00 | Trainee 01 | 23/02/2013 13:14:59 | 7 | TS | P | 2013-05-03 | INSTRUCTED | Trainee 01 | NS - TRANSPORT FOR LONDON | 26/02/2013 |  | 1 | 15/02/2013 13:38:11 |  |  | OM0909 | NE 3rd Party Claims over Â£10k
Late | 15/03/2013 09:10:00 | NE1_HLSR/19 | 428579 | ACCD | 1A | 15/02/2013 09:10:00 | Test LOHAC NORTH EAST LOAD 1 | HLSR | INS |  |  |  |  | 428579 | INS |  |  |  |  | INS |  | 15/03/2013 09:10:00 | Trainee 01 | 16/03/2013 09:09:59 | 28 | BF | P | 15/03/2013 09:10:00 | INSTRUCTED | Trainee 01 | NS - TRANSPORT FOR LONDON | 26/02/2013 |  | 26.43 | 15/02/2013 15:53:27 |  |  | RA0999 | NE Reactive Activity Lump Sum Defect Rectification
Late | 16/02/2013 13:57:00 | NE1_HLSR/34 | 428580 | DAMM | 1A | 15/02/2013 13:57:00 | TEST AUTOMATION LOAD 1 | HLSR | [5 empty] | 428580 | [8 empty] | Trainee 03 |  | 1 | BF | T | 16/02/2013 13:57:00 | DRAFT | Trainee 03 |  |  |  | 26.43 | 21/02/2013 16:13:26 |  |  | RA0999 | NE Reactive Activity Lump Sum Defect Rectification
Late | 15/03/2013 12:20:00 | NE1_HLSR/25 | 428581 | DAMM | 2M | 15/02/2013 12:20:00 | TEST AUTOMATION LOAD 2 | HLSR | [5 empty] | 428581 | [7 empty] | 15/03/2013 12:20:00 | Trainee 01 | 16/03/2013 12:19:59 | 28 | BF | P | 15/03/2013 12:20:00 | DRAFT | Trainee 01 |  |  |  |  | 18/02/2013 16:38:47 |  |  | RA0999 | NE Reactive Activity Lump Sum Defect Rectification
Late | 22/02/2013 12:20:00 | NE1_HLSR/33 | 428582 | DAMM | 2H | 15/02/2013 12:20:00 | TEST AUTOMATION LOAD 3 | HLSR | [5 empty] | 428582 | [8 empty] | Trainee 01 |  | 7 | BF | P | 22/02/2013 12:20:00 | DRAFT | Trainee 01 |  |  |  |  | 21/02/2013 16:13:40 |  |  | RA0999 | NE Reactive Activity Lump Sum Defect Rectification
Late | 15/03/2013 12:20:00 | NE1_HLSR/32 | 428583 | GRGE | 2M | 15/02/2013 12:20:00 | TEST AUTOMATION LOAD 4 | HLSR | [5 empty] | 428583 | [8 empty] | Trainee 02 |  | 28 | BF | P | 15/03/2013 12:20:00 | DRAFT | Trainee 02 |  |  |  |  | 21/02/2013 16:13:26 |  |  | RA0999 | NE Reactive Activity Lump Sum Defect Rectification
Late | 16/02/2013 09:55:00 | NE1_HLSR/20 | 428585 | CKIR | 1A | 15/02/2013 09:55:00 | TEST LOAD 6 | HLSR | INS |  |  |  |  | 428585 | INS |  |  |  |  | INS |  | 16/02/2013 09:55:00 | Trainee 01 | 17/02/2013 09:54:59 | 1 | CG | T | 16/02/2013 09:55:00 | INSTRUCTED | Trainee 01 | NS - TRANSPORT FOR LONDON | 26/02/2013 |  | 13.79 | 15/02/2013 15:56:57 |  |  | RA0999 | NE Reactive Activity Lump Sum Defect Rectification
Late | 15/03/2013 11:55:00 | NE1_HLSR/45 | 428587 | CKIR | 1A | 15/02/2013 11:55:00 | TEST LOAD 8 | HLSR | INS |  |  |  |  | 428587 | INS |  |  |  |  | INS |  | 15/03/2013 11:55:00 | Trainee 01 | 16/03/2013 11:54:59 | 28 | CG | P | 15/03/2013 11:55:00 | INSTRUCTED | Trainee 01 |  | 27/02/2013 |  | 212.59 | 27/02/2013 12:58:01 |  |  | RA0999 | NE Reactive Activity Lump Sum Defect Rectification
Late | 15/03/2013 14:33:00 | NE1_HLSR/23 | 428588 | MISS | 1A | 15/02/2013 14:33:00 | TEST AUTOMATION LOAD 9 | HLSR | INS |  |  |  |  | 428588 | INS |  |  |  |  | INS |  | 15/03/2013 14:33:00 | Trainee 01 | 16/03/2013 14:32:59 | 28 | BF | P | 15/03/2013 14:33:00 | INSTRUCTED | Trainee 01 | NS - TRANSPORT FOR LONDON | 26/02/2013 10:58:38 |  | 7.74 | 15/02/2013 16:03:34 |  |  | RA0999 | NE Reactive Activity Lump Sum Defect Rectification
Late | 25/02/2013 12:23:00 | NE1_HLSR/24 | 428589 | ACCD | 2H | 18/02/2013 12:23:00 | Test WC File Load - Ordered Maintenance 1 | HLSR | [5 empty] | 428589 | [7 empty] | 25/02/2013 12:23:00 | Trainee 01 | 26/02/2013 12:22:59 | 7 | SG | P | 25/02/2013 12:23:00 | DRAFT | Trainee 01 |  |  |  |  | 18/02/2013 14:14:56 |  |  | RA0999 | NE Reactive Activity Lump Sum Defect Rectification
Late | 21/03/2013 | NE1_SLSR/1 | 428614 | LTEN | 1A | 21/02/2013 | broken safety fence | SLSR | RDY |  |  |  |  | 428614 | RDY |  |  |  |  | RDY |  | 21/03/2013 09:12:00 | Trainee 04 | 22/03/2013 09:11:59 | 28 | FB | P | 21/03/2013 | DRAFT | Trainee 04 |  |  |  | 59.15 | 21/02/2013 14:17:55 |  |  | RA0999 | NE Reactive Activity Lump Sum Defect Rectification
Late | 18/03/2013 | NE1_HLSR/29 | 428615 | LOSB | 1A | 18/02/2013 | its broke init | HLSR | RDY |  |  |  |  | 428615 | RDY |  |  |  |  | RDY |  | 18/03/2013 12:00:00 | Trainee 06 | 19/03/2013 11:59:59 | 28 | FF | P | 18/03/2013 | DRAFT | Trainee 06 |  |  |  |  | 21/02/2013 14:18:50 |  |  | RA0999 | NE Reactive Activity Lump Sum Defect Rectification
Late | 21/02/2013 | NE1_HLSC/6 | 428617 | CCTP | 2H | 14/02/2013 |  | HLSC | RDY |  |  |  |  | 428617 | RDY |  |  |  |  | RDY |  | 21/02/2013 | Trainee 05 | 21/02/2013 23:59:59 | 7 | BT | P | 21/02/2013 | DRAFT | Trainee 05 |  |  |  | 15.82 | 21/02/2013 14:19:47 |  |  | RA0999 | NE Reactive Activity Lump Sum Defect Rectification
Late | 28/02/2013 | NE1_HLSR/28 | 428619 | MIRF | 2H | 21/02/2013 |  | HLSR | [5 empty] | 428619 | [7 empty] | 28/02/2013 | Trainee 02 | 28/02/2013 23:59:59 | 7 | RM | P | 28/02/2013 | DRAFT | Trainee 02 |  |  |  | 223.35 | 21/02/2013 14:13:06 |  |  | RA0999 | NE Reactive Activity Lump Sum Defect Rectification
Late | 25/03/2013 10:01:00 | NE1_HLSR/42 | 428623 | BLCK | 2M | 25/02/2013 10:01:00 | Test Cancellation of a Works Order - Defect Description | HLSR | RDY |  |  |  |  | 428623 | RDY |  |  |  |  | RDY |  | 25/03/2013 10:01:00 | Trainee 02 | 26/03/2013 10:00:59 | 28 | CM | P | 25/03/2013 10:01:00 | DRAFT | Trainee 02 | NS - TEST |  |  | 1 | 27/02/2013 12:40:11 |  |  | RA0999 | NE Reactive Activity Lump Sum Defect Rectification
Late | 2013-04-03 10:21 | NE1_HLSR/41 | 428624 | CCTF | 2H | 25/02/2013 10:21:00 | Test cancellation of a defect - Defect Description | HLSR | RDY |  |  |  |  | 428624 | RDY |  |  |  |  | RDY |  | 2013-04-03 10:21 | Trainee 01 | 2013-05-03 10:21 | 7 | BF | P | 2013-04-03 10:21 | DRAFT | Trainee 01 | NS - TEST |  |  | 1 | 27/02/2013 12:34:27 |  |  | RA0999 | NE Reactive Activity Lump Sum Defect Rectification
Late | 2013-01-03 | NE1_HLSR/43 | 428625 | CCTP | 2H | 25/02/2013 10:30:00 | TEST DEFECT DSECRIPTION | HLSR | INS | APP | 1060 | 2013-01-03 |  | 428625 | INS | UTL |  |  |  | INS |  | 2013-04-03 10:30 | Trainee 01 | 2013-01-03 | 7 | BF | P | 2013-01-03 | INSTRUCTED | Trainee 01 |  | 27/02/2013 17:15:41 |  | 1 | 27/02/2013 12:40:43 |  |  | RA0999 | NE Reactive Activity Lump Sum Defect Rectification
Late | 2013-04-03 12:51 | NE1_SLSR/2 | 428630 | CRCK | 2H | 25/02/2013 12:51:00 | Test Defect Description - Works Order Draft Status 2 | SLSR | RDY |  |  |  |  | 428630 | RDY |  |  |  |  | RDY |  | 2013-04-03 12:51 | Trainee 01 | 2013-05-03 12:51 | 7 | CM | P | 2013-04-03 12:51 | DRAFT | Trainee 01 |  |  |  | 26.43 | 25/02/2013 12:51:46 |  |  | OM0909 | NE 3rd Party Claims over Â£10k
Late | 2013-01-03 | NE1_HLSR/44 | 428643 | POTH | 1E | 2013-01-02 | description text | HLSR | INS |  |  |  |  | 428643 | INS |  |  |  |  | INS |  | 2013-01-03 10:00 | Trainee 04 | 2013-02-03 10:00 | 28 | MC | P | 2013-01-03 | INSTRUCTED | Trainee 04 |  | 27/02/2013 17:11:48 |  | 151.31 | 27/02/2013 12:57:50 |  |  | RA0999 | NE Reactive Activity Lump Sum Defect Rectification
Late | 2013-07-03 10:19 | NE1_HLSR/47 | 428660 | POTH | 2H | 28/02/2013 10:19:00 |  | HLSR | INS |  |  |  |  | 428660 | INS |  |  |  |  | INS |  | 2013-07-03 10:19 | Trainee 04 | 2013-08-03 10:19 | 7 | FC | P | 2013-07-03 10:19 | INSTRUCTED | Trainee 04 |  | 28/02/2013 |  | 1218.84 | 28/02/2013 10:04:29 |  |  | RA0999 | NE Reactive Activity Lump Sum Defect Rectification
Late | 2013-04-04 10:08 | NE1_HLSR/80 | 428723 | CRCK | 1 | 2013-04-04 09:08 |  | HLSR | INS |  |  |  |  | 428723 | INS |  |  |  |  | INS |  | 2013-04-04 10:08 | LOHACNE1 | 2013-05-04 10:08 | 0.041667 | CM | T | 2013-04-04 10:08 | INSTRUCTED | LOHACNE1 |  | 2013-04-04 09:20 |  | 9.97 | 2013-04-04 09:19 |  |  | RA0999 | NE Reactive Activity Lump Sum Defect Rectification
Late | 2013-04-04 | NE1_HLSR/84 | 428727 | ACCD | 2H | 2013-04-04 09:47 |  | HLSR |  | APP | 1060 | 2013-04-04 |  | 428727 |  | UTL | [5 empty] | 2013-11-04 09:47 | SYSTEM ADMINISTRATOR | 2013-04-04 | 7 | BF | P | 2013-04-04 | INSTRUCTED | SYSTEM ADMINISTRATOR |  |  |  | 26.43 | 2013-04-04 09:50 |  |  | RA0999 | NE Reactive Activity Lump Sum Defect Rectification
Late | 2013-01-03 | NE1_HLSR/51 | [5 empty] | HLSR | INS | APF | 1258 | 2013-01-03 |  |  | INS | UPC |  |  |  | INS |  |  | Trainee 01 | 2013-01-03 | 0 | 0 |  | 2013-01-03 | INSTRUCTED | Trainee 01 |  | 2013-01-03 14:39 | 0 | 0 | 2013-01-03 13:58 |  |  | RA0999 | NE Reactive Activity Lump Sum Defect Rectification
Late | 2013-01-03 | NE1_HLSR/50 | [5 empty] | HLSR | INS | APF | 1258 | 2013-01-03 |  |  | INS | UPC |  |  |  | INS |  |  | Trainee 01 | 2013-01-03 | 0 | 0 |  | 2013-01-03 | INSTRUCTED | Trainee 01 |  | 2013-01-03 14:39 | 0 | 0 | 2013-01-03 13:56 |  |  | RA0999 | NE Reactive Activity Lump Sum Defect Rectification
Late | 23/02/2013 | NE1_HLSR/73 | [5 empty] | HLSR | INS | APF | 1258 | 23/02/2013 |  |  | INS | ADJ |  |  |  | INS |  |  | Trainee 01 | 23/02/2013 | 0 | 0 |  | 23/02/2013 | INSTRUCTED | Trainee 01 |  | 2013-01-03 14:41 | 0 | 0 | 2013-01-03 14:33 |  |  | RA0999 | NE Reactive Activity Lump Sum Defect Rectification
Late | 23/02/2013 | NE1_HLSR/71 | [5 empty] | HLSR | INS | APF | 1258 | 23/02/2013 |  |  | INS | ADJ |  |  |  | INS |  |  | Trainee 01 | 23/02/2013 | 0 | 0 |  | 23/02/2013 | INSTRUCTED | Trainee 01 |  | 2013-01-03 14:41 | 0 | 0 | 2013-01-03 14:31 |  |  | RA0999 | NE Reactive Activity Lump Sum Defect Rectification
Late | 23/02/2013 | NE1_HLSR/72 | [5 empty] | HLSR | INS | APF | 1258 | 23/02/2013 |  |  | INS | ADJ |  |  |  | INS |  |  | Trainee 01 | 23/02/2013 | 0 | 0 |  | 23/02/2013 | INSTRUCTED | Trainee 01 |  | 2013-01-03 14:41 | 0 | 0 | 2013-01-03 14:33 |  |  | RA0999 | NE Reactive Activity Lump Sum Defect Rectification
Late | 22/02/2013 | NE1_HLSR/74 | [5 empty] | HLSR | INS | APF | 1258 | 22/02/2013 |  |  | INS | ADJ |  |  |  | INS |  |  | Trainee 01 | 22/02/2013 | 0 | 0 |  | 22/02/2013 | INSTRUCTED | Trainee 01 |  | 2013-01-03 14:41 | 0 | 0 | 2013-01-03 14:34 |  |  | RA0999 | NE Reactive Activity Lump Sum Defect Rectification
Late | 2013-01-03 | NE1_HLSR/52 | [5 empty] | HLSR | INS | APF | 1258 | 2013-01-03 |  |  | INS | UPC |  |  |  | INS |  |  | Trainee 01 | 2013-01-03 | 0 | 0 |  | 2013-01-03 | INSTRUCTED | Trainee 01 |  | 2013-01-03 14:39 | 0 | 0 | 2013-01-03 14:04 |  |  | RA0999 | NE Reactive Activity Lump Sum Defect Rectification
Late | 2013-01-03 | NE1_HLSR/49 | [5 empty] | HLSR | INS | APF | 1258 | 2013-01-03 |  |  | INS | UPC |  |  |  | INS |  |  | Trainee 01 | 2013-01-03 | 0 | 0 |  | 2013-01-03 | INSTRUCTED | Trainee 01 |  | 2013-01-03 14:39 |  | 0 | 2013-01-03 13:50 |  |  | RA0999 | NE Reactive Activity Lump Sum Defect Rectification
Late | 28/02/2013 | NE1_HLSR/53 | [5 empty] | HLSR | INS | APF | 1258 | 28/02/2013 |  |  | INS | STR |  |  |  | INS |  |  | Trainee 01 | 28/02/2013 | 0 | 0 |  | 28/02/2013 | INSTRUCTED | Trainee 01 |  | 2013-01-03 14:39 | 0 | 0 | 2013-01-03 14:05 |  |  | RA0999 | NE Reactive Activity Lump Sum Defect Rectification
Late | 28/02/2013 | NE1_HLSR/54 | [5 empty] | HLSR | INS | APF | 1258 | 28/02/2013 |  |  | INS | STR |  |  |  | INS |  |  | Trainee 01 | 28/02/2013 | 0 | 0 |  | 28/02/2013 | INSTRUCTED | Trainee 01 |  | 2013-01-03 14:39 | 0 | 0 | 2013-01-03 14:06 |  |  | RA0999 | NE Reactive Activity Lump Sum Defect Rectification
Late | 28/02/2013 | NE1_HLSR/56 | [5 empty] | HLSR | INS | APF | 1258 | 28/02/2013 |  |  | INS | STR |  |  |  | INS |  |  | Trainee 01 | 28/02/2013 | 0 | 0 |  | 28/02/2013 | INSTRUCTED | Trainee 01 |  | 2013-01-03 14:39 | 0 | 0 | 2013-01-03 14:09 |  |  | RA0999 | NE Reactive Activity Lump Sum Defect Rectification
Late | 28/02/2013 | NE1_HLSR/55 | [5 empty] | HLSR | INS | APF | 1258 | 28/02/2013 |  |  | INS | STR |  |  |  | INS |  |  | Trainee 01 | 28/02/2013 | 0 | 0 |  | 28/02/2013 | INSTRUCTED | Trainee 01 |  | 2013-01-03 14:39 | 0 | 0 | 2013-01-03 14:08 |  |  | RA0999 | NE Reactive Activity Lump Sum Defect Rectification
Late | 27/02/2013 | NE1_HLSR/57 | [5 empty] | HLSR | INS | APF | 1258 | 27/02/2013 |  |  | INS | NSS |  |  |  | INS |  |  | Trainee 01 | 27/02/2013 | 0 | 0 |  | 27/02/2013 | INSTRUCTED | Trainee 01 |  | 2013-01-03 14:40 | 0 | 0 | 2013-01-03 14:15 |  |  | RA0999 | NE Reactive Activity Lump Sum Defect Rectification
Late | 27/02/2013 | NE1_HLSR/58 | [5 empty] | HLSR | INS | APF | 1258 | 27/02/2013 |  |  | INS | NSS |  |  |  | INS |  |  | Trainee 01 | 27/02/2013 | 0 | 0 |  | 27/02/2013 | INSTRUCTED | Trainee 01 |  | 2013-01-03 14:40 | 0 | 0 | 2013-01-03 14:17 |  |  | RA0999 | NE Reactive Activity Lump Sum Defect Rectification
Late | 27/02/2013 | NE1_HLSR/59 | [5 empty] | HLSR | INS | APF | 1258 | 27/02/2013 |  |  | INS | NSS |  |  |  | INS |  |  | Trainee 01 | 27/02/2013 | 0 | 0 |  | 27/02/2013 | INSTRUCTED | Trainee 01 |  | 2013-01-03 14:40 | 0 | 0 | 2013-01-03 14:19 |  |  | RA0999 | NE Reactive Activity Lump Sum Defect Rectification
Late | 27/02/2013 | NE1_HLSR/60 | [5 empty] | HLSR | INS | APF | 1258 | 27/02/2013 |  |  | INS | NSS |  |  |  | INS |  |  | Trainee 01 | 27/02/2013 | 0 | 0 |  | 27/02/2013 | INSTRUCTED | Trainee 01 |  | 2013-01-03 14:40 | 0 | 0 | 2013-01-03 14:19 |  |  | RA0999 | NE Reactive Activity Lump Sum Defect Rectification
Late | 26/02/2013 | NE1_HLSR/61 | [5 empty] | HLSR | INS | APF | 1258 | 26/02/2013 |  |  | INS | UTL |  |  |  | INS |  |  | Trainee 01 | 26/02/2013 | 0 | 0 |  | 26/02/2013 | INSTRUCTED | Trainee 01 |  | 2013-01-03 14:40 | 0 | 0 | 2013-01-03 14:20 |  |  | RA0999 | NE Reactive Activity Lump Sum Defect Rectification
Late | 26/02/2013 | NE1_HLSR/63 | [5 empty] | HLSR | INS | APF | 1258 | 26/02/2013 |  |  | INS | UTL |  |  |  | INS |  |  | Trainee 01 | 26/02/2013 | 0 | 0 |  | 26/02/2013 | INSTRUCTED | Trainee 01 |  | 2013-01-03 14:40 | 0 | 0 | 2013-01-03 14:22 |  |  | RA0999 | NE Reactive Activity Lump Sum Defect Rectification
Late | 26/02/2013 | NE1_HLSR/64 | [5 empty] | HLSR | INS | APF | 1258 | 26/02/2013 |  |  | INS | UTL |  |  |  | INS |  |  | Trainee 01 | 26/02/2013 | 0 | 0 |  | 26/02/2013 | INSTRUCTED | Trainee 01 |  | 2013-01-03 14:40 | 0 | 0 | 2013-01-03 14:23 |  |  | RA0999 | NE Reactive Activity Lump Sum Defect Rectification
Late | 26/02/2013 | NE1_HLSR/62 | [5 empty] | HLSR | INS | APF | 1258 | 26/02/2013 |  |  | INS | UTL |  |  |  | INS |  |  | Trainee 01 | 26/02/2013 | 0 | 0 |  | 26/02/2013 | INSTRUCTED | Trainee 01 |  | 2013-01-03 14:40 | 0 | 0 | 2013-01-03 14:21 |  |  | RA0999 | NE Reactive Activity Lump Sum Defect Rectification
Late | 25/02/2013 | NE1_HLSR/65 | [5 empty] | HLSR | INS | APF | 1258 | 25/02/2013 |  |  | INS | DNF |  |  |  | INS |  |  | Trainee 01 | 25/02/2013 | 0 | 0 |  | 25/02/2013 | INSTRUCTED | Trainee 01 |  | 2013-01-03 14:41 | 0 | 0 | 2013-01-03 14:24 |  |  | RA0999 | NE Reactive Activity Lump Sum Defect Rectification
Late | 25/02/2013 | NE1_HLSR/66 | [5 empty] | HLSR | INS | APF | 1258 | 25/02/2013 |  |  | INS | DNF |  |  |  | INS |  |  | Trainee 01 | 25/02/2013 | 0 | 0 |  | 25/02/2013 | INSTRUCTED | Trainee 01 |  | 2013-01-03 14:41 | 0 | 0 | 2013-01-03 14:25 |  |  | RA0999 | NE Reactive Activity Lump Sum Defect Rectification
Late | 25/02/2013 | NE1_HLSR/67 | [5 empty] | HLSR | INS | APF | 1258 | 25/02/2013 |  |  | INS | DNF |  |  |  | INS |  |  | Trainee 01 | 25/02/2013 | 0 | 0 |  | 25/02/2013 | INSTRUCTED | Trainee 01 |  | 2013-01-03 14:41 | 0 | 0 | 2013-01-03 14:26 |  |  | RA0999 | NE Reactive Activity Lump Sum Defect Rectification
Late | 24/02/2013 | NE1_HLSR/68 | [5 empty] | HLSR | INS | APF | 1258 | 24/02/2013 |  |  | INS | DNF |  |  |  | INS |  |  | Trainee 01 | 24/02/2013 | 0 | 0 |  | 24/02/2013 | INSTRUCTED | Trainee 01 |  | 2013-01-03 14:41 | 0 | 0 | 2013-01-03 14:27 |  |  | RA0999 | NE Reactive Activity Lump Sum Defect Rectification
Late | 24/02/2013 | NE1_HLSR/70 | [5 empty] | HLSR | INS | APF | 1258 | 24/02/2013 |  |  | INS | DNF |  |  |  | INS |  |  | Trainee 01 | 24/02/2013 | 0 | 0 |  | 24/02/2013 | INSTRUCTED | Trainee 01 |  | 2013-01-03 14:41 | 0 | 0 | 2013-01-03 14:30 |  |  | RA0999 | NE Reactive Activity Lump Sum Defect Rectification
Late | 24/02/2013 | NE1_HLSR/69 | [5 empty] | HLSR | INS | APF | 1258 | 24/02/2013 |  |  | INS | DNF |  |  |  | INS |  |  | Trainee 01 | 24/02/2013 | 0 | 0 |  | 24/02/2013 | INSTRUCTED | Trainee 01 |  | 2013-01-03 14:41 | 0 | 0 | 2013-01-03 14:28 |  |  | RA0999 | NE Reactive Activity Lump Sum Defect Rectification
Late | 2013-04-04 | NE1_HR/103 | [5 empty] | HR | INS | APF | 1060 | 2013-04-04 |  |  | INS | UTL |  |  |  | INS |  |  | Trainee 01 | 2013-04-04 | 0 | 0 |  | 2013-04-04 | INSTRUCTED | Trainee 01 |  | 28/03/2013 | 0 | 9 | 2013-01-03 14:56 |  |  | OM0905 | NE Vegetative & Arboriculture
Late | 2013-08-02 | NE1_HTO/11 | [5 empty] | HTO | [12 empty] | 2013-08-02 |  | Trainee 01 |  | 0 | 0 |  | 2013-08-02 | DRAFT | Trainee 01 |  |  |  |  | 27/02/2013 11:01:52 |  |  | DU0002 | Highways Task Order Request Dummy Budget
Late | 27/02/2013 | NE1_HTO/18 | [5 empty] | HTO | [12 empty] | 27/02/2013 |  | Trainee 01 |  | 0 | 0 |  | 27/02/2013 | DRAFT | Trainee 01 |  |  |  |  | 27/02/2013 11:14:54 |  |  | DU0002 | Highways Task Order Request Dummy Budget
Late | 28/02/2013 | NE1_HTO/10 | [5 empty] | HTO | [12 empty] | 28/02/2013 |  | Trainee 01 |  | 0 | 0 |  | 28/02/2013 | DRAFT | Trainee 01 |  |  |  |  | 27/02/2013 10:59:46 |  |  | DU0002 | Highways Task Order Request Dummy Budget
Late | 2013-01-03 | NE1_HTO/14 | [5 empty] | HTO | [12 empty] | 2013-01-03 |  | Trainee 01 |  | 0 | 0 |  | 2013-01-03 | DRAFT | Trainee 01 |  |  |  |  | 27/02/2013 11:07:42 |  |  | DU0002 | Highways Task Order Request Dummy Budget
Late | 2013-04-03 | NE1_HTO/17 | [5 empty] | HTO | [12 empty] | 2013-04-03 |  | Trainee 01 |  | 0 | 0 |  | 2013-04-03 | DRAFT | Trainee 01 |  |  |  |  | 27/02/2013 11:12:44 |  |  | DU0002 | Highways Task Order Request Dummy Budget
Late | 2013-07-03 | NE1_HTO/5 | [5 empty] | HTO | [12 empty] | 2013-07-03 |  | Trainee 01 |  | 0 | 0 |  | 2013-07-03 | DRAFT | Trainee 01 | NS - TRANSPORT FOR LONDON |  | 0 | 42.78 | 15/02/2013 16:30:23 |  |  | GI0901 | NE General Inspections
Late | 2013-08-03 | NE1_HTO/16 | [5 empty] | HTO | [12 empty] | 2013-08-03 |  | Trainee 01 |  | 0 | 0 |  | 2013-08-03 | DRAFT | Trainee 01 |  |  |  |  | 27/02/2013 11:11:12 |  |  | DU0002 | Highways Task Order Request Dummy Budget
Late | 2013-11-03 | NE1_HTO/15 | [5 empty] | HTO | [12 empty] | 2013-11-03 |  | Trainee 01 |  | 0 | 0 |  | 2013-11-03 | DRAFT | Trainee 01 |  |  |  |  | 27/02/2013 11:09:21 |  |  | DU0002 | Highways Task Order Request Dummy Budget
Late | 22/03/2013 | NE1_HTO/12 | [5 empty] | HTO | [12 empty] | 22/03/2013 |  | Trainee 01 |  | 0 | 0 |  | 22/03/2013 | DRAFT | Trainee 01 |  |  |  |  | 27/02/2013 11:03:49 |  |  | DU0002 | Highways Task Order Request Dummy Budget
Late | 25/03/2013 | NE1_HTO/13 | [5 empty] | HTO | [12 empty] | 25/03/2013 |  | Trainee 01 |  | 0 | 0 |  | 25/03/2013 | DRAFT | Trainee 01 |  |  |  |  | 27/02/2013 11:05:48 |  |  | DU0002 | Highways Task Order Request Dummy Budget
Late | 29/03/2013 | NE1_HTO/19 | [5 empty] | HTO | [12 empty] | 29/03/2013 |  | Trainee 01 |  | 0 | 0 |  | 29/03/2013 | DRAFT | Trainee 01 |  |  |  |  | 27/02/2013 11:16:55 |  |  | DU0002 | Highways Task Order Request Dummy Budget
Late | 29/03/2013 | NE1_HTO/20 | [5 empty] | HTO | [12 empty] | 29/03/2013 |  | Trainee 01 |  | 0 | 0 |  | 29/03/2013 | DRAFT | Trainee 01 |  |  |  |  | 27/02/2013 11:18:54 |  |  | DU0002 | Highways Task Order Request Dummy Budget
Late | 30/03/2013 | NE1_HTO/65 | [5 empty] | HTO | [12 empty] | 30/03/2013 |  | Trainee 07 |  | 0 | 0 |  | 30/03/2013 | DRAFT | Trainee 07 |  |  |  |  | 28/03/2013 11:40:18 |  |  | DU0002 | Highways Task Order Request Dummy Budget
Late | 31/03/2013 | NE1_HTO/73 | [5 empty] | HTO | [12 empty] | 31/03/2013 |  | Trainee 09 |  | 0 | 0 |  | 31/03/2013 | DRAFT | Trainee 09 |  |  |  |  | 28/03/2013 11:41:22 |  |  | DU0002 | Highways Task Order Request Dummy Budget
Late | 2013-01-04 | NE1_HTO/21 | [5 empty] | HTO | [12 empty] | 2013-01-04 |  | Trainee 01 |  | 0 | 0 |  | 2013-01-04 | DRAFT | Trainee 01 |  |  |  |  | 27/02/2013 11:20:24 |  |  | DU0002 | Highways Task Order Request Dummy Budget