## Issues
| Known Post Live Issues/Changes |  |  | Hint: use ALT+ Enter when making comments to begin a new line in the cell
Item Number | POD_FAMILY | POD TITLE | POD SERIES | ISSUE | Reported By | Environment Tested | Example W/O # | PRIORITY | STATUS | CSL/TFL Comment | Bentley Comment | Fix Issued to PRD
1 | IM_LOHAC_AR_00_TOP | Application Review | APP REJ | Items do not move to the appropriate status when changed to Approved or to Rejected |  | TST |  |  | Awaiting More Information | I have logged in as a user who has the appropriate roles to update the Invoice Status field to Approved or Rejected. I am able to successfully update works orders within the application to approved or rejected but if I try to update works orders to this status within IM4 then the save does not change | Mendoza(3/may): TST does not have the fix 7 version of xtfl_wo_sec_u_trg.sql applied. BUT, I noticed that the version installed no longer changes dates. Should it change dates or shouldn’t it.
2 | IM_LOHAC_AR_00_TOP | Application Review |  | The map image is not displayed in the Awaiting Review stack for Ordered Maintenance Works Orders i.e. a square with a red cross is displayed | NS | TST |  |  | Awaiting More Information |  | Mendoza(3/may): Unable to properly test on TST, user LOHACNE1/FIX7TEST failed But uses same image location as the WOWT pods, so I would expect those to fail as well if this one is failing
3 | IM_LOHAC_AR_00_TOP | Application Review |  | If I update the Invoice Status field to be anything except for Approved or Rejected then the INVOICE_STATUS_UPDATE (flexible attribute) field is not being updated to reflect the date that the change was made i.e. if I try to update the field to Rejected and I don't have the correct role then it resets this back to what it was before this change which is correct and the works order is displayed in the 0-1 column because I tried to make this change today however if I try to update the status to Rejected - Awaiting Commercial Review then the status updates as it should but the works order is still displayed in the day banding it was originally i.e. the INVOICE_STATUS_UPDATE field is not updated by the trigger to todays date. Does the trigger only update the date if you try to update the Invoice Status flexible attribute field to Approved or Rejected? | NS | TST |  |  | Awaiting More Information |  | Mendoza(3/may): This is related to the xtfl_wo_sec_u_trg that is mentioned in Item Number 1. Are there reasons the trigger changed?
4 | IM41015 | EOT-REQUEST | Initial Repeat | Works Orders are still displaying on the EOT Request POD once the EOT Status has been updated to Approved, Rejected or Conditional within the LoHAC Production environment |  | TST |  |  | Passed Test - Awaiting TFL Approval | Test successful and is ready for deployment into PRD - please provide the necessary script for CSL to run within PRD | Mendoza: Now filtering statuses of: APP, REJ,CND
5 | IM41020 | Work Order Due to be Completed | LUMP SUM | Awaiting New CSL Comments or to mark complete |  | TST |  |  | Passed Test - Awaiting TFL Approval | Ready for Review by TfL prior to deployment into PRD. Please prepare the necessary script for this POD to be deployed into PRD by CSL
6 | IM41021 | Work Order Due to be Completed | NON LUMP SUM | Awaiting New CSL Comments |  | TST |  |  | Passed Test - Awaiting TFL Approval | Ready for Review by TfL prior to deployment into PRD. Please prepare the necessary script for this POD to be deployed into PRD by CSL
7 | IM41022 | Work Order Due to be Completed | NON DEFECT | Awaiting New CSL Comments |  | TST |  |  | Passed Test - Awaiting TFL Approval | Ready for Review by TfL prior to deployment into PRD. Please prepare the necessary script for this POD to be deployed into PRD by CSL
8 | IM41035 | Rejected Work Orders | TOR | The Column does not take Task Order Status into account | JMM | TST |  |  | Ready for test | Can you provide further details on this change? | The Task Order Request Series did not check to see if WOR_CHAR_ATTRIB118 had a value in it
9 | IM41036 | Held Work Orders | TOR | The Column does not take Task Order Status into account | JMM | TST |  |  | Ready for test | Can you provide further details on this change? | The Task Order Request Series did not check to see if WOR_CHAR_ATTRIB118 had a value in it
10 | IM41040 | Updated EOTs | TOR | The Column does not take Task Order Status into account | JMM | TST |  |  | Ready for test | Can you provide further details on this change? | The Task Order Request Series did not check to see if WOR_CHAR_ATTRIB118 had a value in it
11 | WOWT001 | Works Order to Instruct | ALL | Within the Works Order to Instruct POD there are some works orders (which do have a works order line and a budget and the Task Order Status is null) appearing within the Task Order Status stack. These works orders should be displayed in the appropriate stack based upon their priority i.e. 2M etc. – only works orders without lines and budgets and where the task order status field is populated should be displayed in the Task Order Request stack. |  | TST |  |  | Passed Test - Awaiting TFL Approval |  | Mendoza: Modified Underlining Query, and the TOR Series on the POD
12 | WOWT003 | Works Order - Draft Status | ALL | As we understand it the logic for the Task Order Request stack in the Works Order - Draft Status POD is: If the works order does not have a line and a budget and the Task Order Status (flexible attribute) field is populated with a value then it appears in the Task Order Request stack. As soon as it does have a line and a budget then it moves to the Non Lump Sum stack. TfL would like this logic changed so that if a Works Order does have a line and a budget and the Task Order Status (flexible attribute) field is set to PROD (Quote Produced) or DRAFT (Draft Quote) it should remain in the Task Order Request stack. |  | TST |  |  | Ready for test | In order to test this I created two new Task Orders which do not have a line and budget. The Task Order Status field is populated however the works orders are no longer displaying on the Works Order - Draft Status POD - examples have been provided | Belived to be resolved
13 | WOWT003 | Works Order - Draft Status | ALL | If a works order has a Permanent and a Temporary Repair where one of these are instructed and the other draft then the works order will not appear on the Works Order - Draft Status POD |  |  |  |  | Ready for test |  | Mendoza(3/may): Please retest in fix 7
14 | WOWT003 | Work Orders - Draft Status | TOR | The Column does not take Task Order Status into account | JMM | TST |  |  | Ready for test | Can you provide further details on this change? | The Task Order Request Series did not check to see if WOR_CHAR_ATTRIB118 had a value in it
15 | WOWT003 | Works Order - Draft Status POD |  | The display of the Works Order - Draft Status POD has changed so that the stacks are not stacked |  | TST |  |  | Ready for test |  | Mendoza(3/may): Appears correct in TST, ready fro review
16 | IM_LOHAC_AS_00_TOP | Application Status |  | If I click on any stacks within this POD then the work tray says that there is no data to display even though records are displayed within the graph | NS | TST |  |  | Awaiting More Information |  | Mendoza(3/may): Unable to properly test on TST, user LOHACNE1/FIX7TEST failed
17 | N/A | All PODS |  | The document previews are not displayed within the Document Pop Up screen | NS | TST |  |  | In Progress |  | Mendoza(3/May): This is most likely not IM4 related but product options related. I need to talk with other team members to locate the appropriate documentation
18 | WOWT001 | Works Order to Instruct | ALL | Speed issue when loading POD | JC | PRD |  |  | Ready for test |  | Mendoza: Added 2 indexes (for wowt003 and wowt001) Would like John Cook to review in TST before I spend more time on it
19 | WOWT003 | Works Order - Draft Status | ALL | Speed issue when loading POD | JC | PRD |  |  | Ready for test |  | Mendoza: Added 2 indexes (for wowt003 and wowt001) Restructured Budgeted SQL for this pod Would like John Cook to review in TST before I spend more time on it
Note on I3: Author: Please number the order that you would like these addressed in

## Resolved Issues
Known Post Live Issues/Changes |  |  | Hint: use ALT+ Enter when making comments to begin a new line in the cell
POD_FAMILY | POD TITLE | POD SERIES | ISSUE | PRIORITY | STATUS | CSL/TFL Comment | Bentley Comment
Note on E3: Author: Please number the order that you would like these addressed in

## Valuelookup
Status
In Progress
Ready for test
Test Failed
Not Started
Passed Test - Awaiting TFL Approval
Resolved
Awaiting More Information