## Sheet1
Defect ID | POD | Issues | MENDOZA | Comments | Is this an issue on TST? | Example Works Order Numbers
|  |  | COMMENTS |  |  | PRD | TST
1 | Available Defects | The base maps are not displayed when you click the map button and the map pop up appears | The Map tab is not working. T.F: this is either a Mapviewer Configuration issue, or the wrong URL is in IM4 |  | N | N | N/A
4 | Works Order - Draft Status | The base maps are not displayed when you click the map button and the map pop up appears | The Map tab is not working. T.F: this is either a Mapviewer Configuration issue, or the wrong URL is in IM4 |  | N | N | N/A
6 | Works Order to Instruct | The base maps are not displayed when you click the map button and the map pop up appears | The Map tab is not working. T.F: this is either a Mapviewer Configuration issue, or the wrong URL is in IM4 |  | N | N | N
8 | Held Works Orders | If you select any of the following reasons within the Works Order Process Status Reason field then the works order is not displayed on the POD: BOQINV CCINV 3RDDAM NOPOT NODEFVIS INCDEFPRI TOHELD | Unable to troubleshoot due to connection issues to PRD |  | N | N/A | N/A
10 |  | The base maps are not displayed when you click the map button and the map pop up appears | The Map tab is not working. T.F: this is either a Mapviewer Configuration issue, or the wrong URL is in IM4 |  | N | N | N
27 |  | I have updated some works orders so that they will appear in the Today column in the Held Works Order POD. They do appear however they are also duplicated in the 1-6 column also. | Issue is Resolved
11 |  | Works Orders without lines and budgets are not displayed | Issue is Resolved |  | N
12 | Rejected Works Orders | If you select any of the following reasons within the Works Order Process Status Reason field then the works order is not displayed on the POD: NODEFVIS CNSCHWO | Unable to troubleshoot due to connection issues to PRD |  | Y
13 |  | The base maps are not displayed when you click the map button and the map pop up appears | The Map tab is not working. T.F: this is either a Mapviewer Configuration issue, or the wrong URL is in IM4 |  | N | N | N
15 | Re-Submitted Works Orders | The same 2H works orders are being displayed under the 0-1 and 2-7 day bandings | Issue is Resolved | Login into IM4 in PRD as LOHACNW1 |  | NW1_HR/6
16 |  | The base maps are not displayed when you click the map button and the map pop up appears | The Map tab is not working. T.F: this is either a Mapviewer Configuration issue, or the wrong URL is in IM4 |  | N | N | N
17 | Works Order Due to be Completed | Unable to get any data to appear in the Non Defect Works Order stack. An HR contract type works order has been created with a works order line and budget but no defect and the appropriate flexible attribute fields have been populated however the data does not appear in this stack | Issue Resolved (not on PRD) |  | Unable to test because these contract types do not exist in TST | NE1_HR/16 | N/A
18 |  | The base maps are not displayed when you click the map button and the map pop up appears | The Map tab is not working. T.F: this is either a Mapviewer Configuration issue, or the wrong URL is in IM4 |  | N | N/A | N/A
19 |  | Request from TfL: If the EOT Status = ‘Rejected’ (WOR_CHAR_ATTRIB101) then the date calculation should be as follows: Calculation 2 – Lump Sum Defects Date Inspected + Defect repair Priority Calculation 3 – Non Lump Sum Defects Date Instruction + Defect repair Priority | I started the Frame work for this: Nicki, can you please confrim that due date and target date is currently working as expected, I don't belive that target date is. Also can you direct me to: Date Instruction, Defect repair Priority interval and Defect repair Priority date |  | N/A | N/A | N/A
20 | EOT Request | The base maps are not displayed when you click the map button and the map pop up appears | The Map tab is not working. T.F: this is either a Mapviewer Configuration issue, or the wrong URL is in IM4 |  | N | N/A | N/A
21 | Updated EOT | Pricing Extension stack is missing from the graph |  |  | N | N/A | N/A
|  | The base maps are not displayed when you click the map button and the map pop up appears | The Map tab is not working. T.F: this is either a Mapviewer Configuration issue, or the wrong URL is in IM4 |  | N | N/A | N/A
22 | Application Review | Approved but Unreviewed (APPUN) is missing as a stack on the graph | Issue is Resolved (not on PRD) |  | N | N/A | N/A
23 |  | Works Orders are not appearing on the PODS when the Invoice Status field is populated via a trigger - audit records are not being created which means the POD does not display the works order on the graph | No Commet | Issue with audit records not being created when the WI trigger fires
28 |  | I have logged into IM4 as a user with Commercial permissions i.e. With the ASSISTANT_COMMERCIAL_MANAGER role however I am unable to update the Invoice Status field to Rejected or Approved. Each time I try to do this then the field is reset back to what is was previously however if you access the flexible attribute fields within the application by clicking the Navigator link etc then you can update the field as expected and the POD reflects that change. | Which User should I test With?
29 |  | I have updated a works order to have a Rejected status and it is appearing in the 0-1 column as well as the 2-7 column. | Issue is Resolved (not on PRD)
24 | Application Status | Approved but Unreviewed (APPUN) is missing as a stack on the graph | Issue is Resolved (not on PRD) |  | N | N/A | N/A
25 |  | Works Orders are not appearing on the PODS when the Invoice Status field is populated via a trigger - audit records are not being created which means the POD does not display the works order on the graph | No Commet | Issue with audit records not being created when the WI trigger fires
26 |  | When I click the Rejected stack within the POD then the work tray says there is no data to display even though there is because the stack is displayed within the graph | Need APEX Access (PRD) to test and resolve, belive I found the issue though |  | N | N/A | N/A
30 |  | I have updated a works order to have a Rejected status and it is appearing in the 0-1 column as well as the 2-7 column. | Issue is Resolved (not on PRD)