## Sheet1
|  | Duration | Hours
Functional Spec Design
| Asset |  | 6 |  | 7.5
| GIS Themes |  | 4
| CSV Loader |  | 12
| Reports |  | ?4 | Still unknown, not completely ironed out in requirements
Review and Finalize Design
Development
| Asset |  | 16
| GIS Themes |  | 24
| CSV Loader |  | 40
| Reports |  | ?24
Documentation
| Install Guide |  | 12
| Basic User Guide |  | 16
Testing
User Testing in Dev
| Defect Fixing |  | 24 | Expecting none, but worse case
UAT sign-off
Cutover
| Load into prod |  | 8