## Issues
Known Post Live Issues/Changes |  |  | Hint: use ALT+ Enter when making comments to begin a new line in the cell
POD_FAMILY | POD TITLE | POD SERIES | ISSUE | PRIORITY | STATUS | CSL/TFL Comment | Bentley Comment
WOWT003 | Works Order - Draft Status | ALL | As we understand it the logic for the Task Order Request stack in the Works Order - Draft Status POD is: If the works order does not have a line and a budget and the Task Order Status (flexible attribute) field is populated with a value then it appears in the Task Order Request stack. As soon as it does have a line and a budget then it moves to the Non Lump Sum stack. TfL would like this logic changed so that if a Works Order does have a line and a budget and the Task Order Status (flexible attribute) field is set to PROD (Quote Produced) or DRAFT (Draft Quote) it should remain in the Task Order Request stack.
WOWT003 | Works Order - Draft Status | ALL | If a works order has a Permanent and a Temporary Repair where one of these are instructed and the other draft then the works order will not appear on the Works Order - Draft Status POD |  | In Progress |  | Mendoza: Narrowed down the issue, working with Clive T to work out how to deal with the issue.
WOWT001 | Works Order to Instruct | ALL | Within the Works Order to Instruct POD there are some works orders (which do have a works order line and a budget and the Task Order Status is null) appearing within the Task Order Status stack. These works orders should be displayed in the appropriate stack based upon their priority i.e. 2M etc. – only works orders without lines and budgets and where the task order status field is populated should be displayed in the Task Order Request stack.
IM41015 | EOT-REQUEST | Initial Repeat | Works Orders are still displaying on the EOT Request POD once the EOT Status has been updated to Approved, Rejected or Conditional within the LoHAC Production environment
IM_LOHAC_AR_00_TOP | Application Review | APP REJ | Items do not move to the appropriate status when changed to Approved or to Rejected |  | Ready for test |  | Mendoza: Had to adjust trigger xtfl_wo_sec_u_trg to function correctly with IM4
IM41020 | Work Order Due to be Completed | LUMP SUM | Awaiting New CSL Comments or to mark complete |  | Ready for test
IM41021 | Work Order Due to be Completed | NON LUMP SUM | Awaiting New CSL Comments |  | Ready for test
IM41022 | Work Order Due to be Completed | NON DEFECT | Awaiting New CSL Comments |  | Ready for test
Note on E3: Author: Please number the order that you would like these addressed in

## Resolved Issues
Known Post Live Issues/Changes |  |  | Hint: use ALT+ Enter when making comments to begin a new line in the cell
POD_FAMILY | POD TITLE | POD SERIES | ISSUE | PRIORITY | STATUS | CSL/TFL Comment | Bentley Comment
Note on E3: Author: Please number the order that you would like these addressed in

## Valuelookup
Status
In Progress
Ready for test
Not Started
Passed Test/Complete