## Sheet2
Section | Task | Notes | Time | Total | days
3.1 | Creation of XAA_ROUTE | Need: get list of datums that make of the route including distance breaks. Then find the min and max slk for the datum inbetween the distance breaks From there build the table | 8 | 188 | 23.5
3.1 | Creation of Spaial veiw/table | Build a geometery for the entire route. Place it in a table, is there an exor API call to do this already? | 4
3.2 | Trigger for XAA_SPATIAL_AUDIT | Trigger on Table: ? On insert: copy newgeoloc to audit table on delete: copy old geoloc to audit table on insert copy new and old geoloc into 2 rows of audit table Do we need more rows addred for the reporting bit (no change report) | 8
4.1 | Creation of input and output tables | XAA_LOC_IDENT XAA_NET_REF | 16
4.1 |  | No change/closed | 16
4.1 |  | newer | 16
4.1 |  | closed | 32
5.1 | Create/populate initial Config tables |  | 16
| code for dynamic SQL |  | 16
| fill table |  | 8
6 | Interface Creation |  | 8
7 | Report | Spilt, merge, reverse, replace, shift, edit | 8
|  | rescall, new segment DB closed, Geometery Update | 8
|  | closed | 8
|  | Recalibrate | 8
|  | Reclassify | 8